## Defect Log
Key | Summary | Component | Severity | Priority | Status | Steps to Reproduce | Expected Result | Actual Result | Linked Test Case(s) | Reporter | Date Found | Date Resolved | Resolution / Fix
DEF-001 | Repeated failed login attempts race with page reload in enter_credentials() | Login | Medium | High | Closed | 1. Open login page. 2. Submit invalid credentials twice in quick succession (as in the 'Repeated failed login attempts' scenario). | Second attempt enters credentials into the reloaded form without error. | NoSuchElementException / stale element reference intermittently thrown because the step tried to type into the pre-reload form. | OEMR-T17 | Automation (flaky CI run) | 2026-08-10 | 2026-08-10 | Added an explicit wait for the username field's visibility at the top of enter_credentials() before typing, so the step waits out the reload instead of racing it.
DEF-002 | Left-nav menu locators used an exact class match and missed real menu items | Navigation | Medium | Medium | Closed | 1. Log in. 2. Run the 'Top-level module menu items are visible' scenario against the live demo. | All documented top-level modules are found via their menu locator. | Locator used exact @class match; the live demo's markup includes additional classes on the same elements, so several modules were reported not found. | OEMR-T23 | Automation (scenario failure) | 2026-08-06 | 2026-08-06 | Relaxed the locator to contains(@class,'menuLabel') so it matches regardless of extra classes.
DEF-003 | pom.xml contained unresolved git merge-conflict markers | Build | Critical | Highest | Closed | 1. Run any mvn command against the checked-in pom.xml. | Maven parses the POM and resolves dependencies normally. | Build failed immediately with a POM parse error -- literal <<<<<<<, =======, >>>>>>> markers were left in the file from an earlier merge. | N/A (build-level, not a Cucumber scenario) | Local build | 2026-08-05 | 2026-08-05 | Manually resolved the conflict and removed the markers, keeping the intended dependency versions.
DEF-004 | Shared public demo (demo.openemr.io) intermittently rejects documented default credentials | Login / Environment | Low | Medium | Monitoring | 1. Run the smoke suite (or PreflightHealthCheck) against demo.openemr.io at an arbitrary time. | admin/pass logs in successfully, as documented by the OpenEMR project. | Login is rejected with 'Invalid username or password' for a period of time; independently confirmed via a manual browser login attempt, so this is the shared demo's own state, not a framework bug. | OEMR-T11 | Automation (CI failure) + manual confirmation | 2026-08-14 |  | Not a code defect -- added PreflightHealthCheck.java as a fast, separate CI step so a demo outage is reported clearly and fails in ~30s instead of the full smoke suite failing confusingly. See utils/PreflightHealthCheck.java. Long-term mitigation: move CI to a self-hosted OpenEMR instance.
DEF-EXAMPLE | <One-line summary of the defect> | <Component, e.g. Patient Management> | <Critical / High / Medium / Low> | <Highest / High / Medium / Low> | <Open / In Progress / Closed / Monitoring> | <Numbered steps to reproduce> | <What should happen> | <What actually happens> | <OEMR-T### key(s) from Test-Case-Register.xlsx> | <Automation / Manual / name> | <YYYY-MM-DD> | <YYYY-MM-DD or blank> | <Root cause and the fix applied, once resolved>